## Tabellenblatt1
SPECCHIO Webinterface – Requirements FHNW IP-516vt, Remo Rossi, Christian Schibli
ID | Requirement | Type | Grouping | Prio (1, 2, 3)* by client | Prio (1, 2, 3)*: Estimation by project team | Sprint | Use Case | Costs (hours) | Risk (0, 1, 2) | Status
1 | The user must be able to search by keyword. | functional | search | 1 | 1 | 1 | 1 | 24 | 1
2 | The user must be able to search by clicking the given pictograms: – Athmosphere – Hydrosphere – Geosphere – Cryosphere – Biosphere | functional | search | 3 | 2 | 4 | 1 |  | 0
3 | The user must be able to search by the SPECCHIO attributes (prefix search). | functional | search | 2 | 2 | 2 | 1 | 16 | 2
4 | The user should be able to search by map. | functional | map search | 3 | 3 | 4 | 1 | 24 | 1
5 | Input for map search are coordinates. | functional | map search | 3 | 3 | 4 | 1 | 4 | 0
6 | Input for map search is location name. | functional | map search | 3 | 3 | 4 | 1 | 4 | 0
7 | The system will notify about no results if the area in km2 exceeds a specific value. | functional | map search | 3 | 2 | 4 | 1 | 12 | 1
8 | The system shows the first 10 results of a search query. | functional | result list | 1 | 1 | 1 | 1 | 16 | 0
9 | Results are initially sorted by date. | non-functional | result list | 1 | 1 | 2 | 1 | 2 | 0
10 | The list of results should contain following information: – date – campaign – owner – name – filename – institute – thumbmail of spectral data diagram – enabled map icon in case of existing map data, disabled if non-existing | functional | result list | 1 | 1 | 2 | 1 | 4 | 0
11 | The system should be able to show a map snippet in the list of results if the mouse pointer is located over an enabled map icon. | functional | result list | 3 | 2 | 3 | 1 | 8 | 1
12 | The user must be able to view 1 spectral data set (simplified). | functional | detail view, map search | 3 | 1 | 3 | 2 | 8 | 1
13 | The user must be able to view 1 spectral data set (fullview –> diagram & metaparameter) | functional | detail view | 1 | 3 | 2 | 2 | 16 | 2
14 | The user should be able to view multiple spectral data sets (fullview). | functional | diagram | 2 | 1 | 2 | 2 | 16 | 1
15 | The user must be able to view detail information about diagram curve from the position where the mouse cursor is currently located. | functional | diagram | 2 | 2 | 3 | 2 | 6 | 1
16 | The user should be able to zoom in into diagram. | functional | diagram | 2 | 2 | 3 | 2 | 4 | 1
17 | Only existing categories should be shown. Categories without content must be fade out. | functional | detail view | 1 | 1 | 2 | 2 | 4 | 0
18 | Spectral data from different types should be separated in different tabs. | functional | detail view | 2 | 3 | 2 | 2 | 4 | 0
19 | File format of spectral data export must be csv (comma-separated values). | functional | data export | 1 | 1 | 2 | 3 | 4 | 0
20 | Multiple data sets from same type must be packed into one csv file. | functional | data export | 1 | 1 | 2 | 3 | 4 | 1
21 | All generated csv files (data sets from different type) must be packed to ZIP. | functional | data export | 2 | 2 | 3 | 3 | 4 | 1
22 | The user must be able to export detail view as PDF. | functional | view export | 2 | 2 | 3 | 4 | 8 | 1
| Version: 1.1 |  | * | Basic requirement | 1 |  | Total | 192
| Date: 10.10.2016 |  |  | Basic requirement 2nd priority | 2
|  |  |  | Nice to have requirement | 3